## Sheet1
ID | Status | In version | Error or new function | Current Prio | Area | Description | Point of attack | Reported by | Prio Anna&Erlend2 | Prio Claus et al | Prio Kee | Branch state | Column1
1 | Closed | 3.9 | Error | 5 |  | When opening a vino-file, make sure to show the top part. Now it scrolls down to the end. | Check “loadNoteDataFromFile” Move caret position to start of “area” |  |  | 5 | 1 | merged into master
2 | Closed | 3.9 | Error | 5 | File handling/selection | Recent files doesn’t work | addRecentFilesInPrefs preferenceChange updateRecentFilesMenu |  |  | 5 | 1 | merged into master
7 | Closed | 3.8 | Error | 6 | Search | Sometimes search does not work - (will investigate more). Cannot scroll text while search field is open. Show if there are no search results. | findText |  |  | 5 | 5 | merged into master
11 | Closed | 3.8 | Error | 5 | Camera commands | Quick Rec / Rec in Vino does not wait for GoPro- Add timeout. So risk of not starting camera when pressing twice. | Check rec status after pressing rec. Revised the whole way of checking gopro ready and gopro recording. Bacpactstatus was used, but it's another command which gives the correct picture. |  |  | 2 | 5 | merged into master
10 | Closed | 3.8 | Error | 5 | Connectivity | Still possible to do time-stamps even if camera is stopped (too hot or other cause). | Check is camera is power-on when inserting timestamp. |  |  | 3 |  | merged into master
4 | Solved with ID7 | 3.8 | Error | 5 | Search | Search does not search unless text field is highlighted. (SAME AS ID 7) | findText |  |  | 5 | 1
5 | Solved with ID7 | 3.8 | Error | 4 | Search | Make it possible to open time-stamps while being in search | Dual focus? Not sure how to attach this one… |  |  | 4 | 1
9 | Part of other | 3.8 | Error | 3 | Connectivity | When changing WIFI from Gopro to VCC, the blue WIFI icon still shows that the camera is connected (even though it is not). Suggestion: Can we monitor if connection to gopro is available? | Same as 10+11.We need to poll the camera to get a status…it’s possible, but difficult to find the right frequency as different situations will influence the optimal polling frequency. Also, consider each request/reply duration. |  |  | 3 | 3 | merged into master
25 | Closed | 3.8 | Error | 5 | UI | video-folder-selection-drop-down håndtaget er forsvundet (dét ‘håndtag’ øverst i tekst-feltet man bruger til at fortælle Vino hvor video filerne ligger) | Fixed as part of ID11
6 | Deferred - handle on PC and Mac |  | Error | 4 |  | Make it possible to open vino files by double-clicking the XML file (consider renaming the file to a .vino file to not open with standard xml viewer). | This is a win/mac thing...change the file extension to for example .vino and associate that with ViNO the application...not sure we can do that on Volvo PC‘s. |  |  | 4 | 1
8 | Open |  | Error | 4 | Import | After import, timestamps still show old file names (even though timestamps work correctly). | markTimestamps |  |  | 4 | 3
14 | Open |  | New function | 4 |  | Add a toggle switch to swith between compiled and un-compiled timestamps. | Real time compile timestamps to avoid having un-compiled timestamps? |  |  | 4 | 3
19 | Open |  | New function | 3 | File handling/selection | Add instructions about moving data from memory card |  |  |  | 3 | 5
15 | Open |  | New function | 3 |  | Add highlight or change cursor to Hand when mouse over button. | Add action handlers in mainEditorView and associate them to mouse over/exit Call setCursor on the scene on primarystage |  |  | 3 | 1
18 | Open |  | New function | 3 | Camera commands | Can we set the time on the GoPro when connecting to the camera? | Check the WIFI API |  |  | 3 | 1
3 | Open |  | Error | 3 |  | Exiting: pressing cancel closes vino | Works on Mac, Win issue? (Claus to recheck on MAC - that is where the issue was) Check “exitApplication” |  |  | 3 | 3
12 | Open |  | Error | 3 |  | If more than 70 files, ”Starting...” won’t disappear. | Look in startRecording() Call to String videoName = mainApp.getGoPro().getMostRecentFileName(); takes too long. |  |  |  | 5
23 | Open |  | Error | 3 | Connectivity | It is possible to insert timestamps even if camera is not recording. | Check is camera is recording when inserting timestamp. |  |  | 3
21 | Open |  | New function | 2 |  | Could we have a copy+compress function? Possibly combined with Merge. |  |  |  | 2 | 1
13 | Open |  | New function | 1 | Import | Remove the Merge-file function if not available (or make it work if possible) | GoPro splits video files into several parts when exceeding a certain size. After importing videos, it is possible to merge the videos. Make this work or remove the function. Remember to update timestamps accordingly. Merge is started with the merge view that will set the mergeflag which indicates a desired merge to take action when ready. The root layout view will check this flag and initiate a post import parsing of the video files directory. Parsing of the directory detects all chaptered (split) files that need merging and call the merge function on each array of chapters. |  |  | 3 | 1
17 | Open |  | New function | 1 | Import | Would it make sense to create a folder structure when importing? | startCopyTask |  |  | 2 | 1
16 | Open |  | New function | 1 | Import | Add a "Stop Import" button. Now you cannot stop the ongoing import and it can take very long time. | Check „startCopyTask” |  |  | 3 | 5
20 | Open |  | New function | 1 | Import | When importing video files, existing files are overwritten (if they were already downloaded once). Can we have a prompt (skip/overwrite)? | handleImportVideoFiles |  |  | 3 | 5
22 | Deferred |  | error | 1 | Import | Naming policy too strict when selecting gopro folder. E.g. "103GOPRO" not accepted. | Should we check the folder at all? Maybe remove the check. Start with setMainApp(MainApp mainApp) public File getGoProDrive() |  |  | 3 |  | branch made. Contains JMTP package + more.
26 | Open |  | Error | 3 |  | If a hashtag exists in the filename, Vino saves file as empty
27 | Open |  | New function | 5 | Upgrade | Upgrade to Gopro 5 support
Note on E1: Prio: 1=low, 3=med, 5=high